## Gantt Chart
Gantt Chart ¦ Ferry Company
PROJECT TITLE |  | Workload Management System for Ferry Company |  |  |  |  | DATE | [8 empty] | 2023-09-14
PROJECT MANAGER |  | Tan Wei Shaun
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | M1 | [27 empty] | M2 | [34 empty] | M3
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | M1
1.1 | Creation of GitHub Repository | Tan Wei Shaun | 2023-09-01 | 2023-09-03 | 2 | 100% | bar: WEEK 1 F to WEEK 1 S; WEEK 2 F to WEEK 2 S
1.2 | Creation of Slack Channel | How Shun Han | 2023-09-01 | 2023-09-03 | 2 | 100% | bar: WEEK 1 F to WEEK 1 S; WEEK 2 F to WEEK 2 S
1.3 | Creation of website template for client meeting | Ong Jun Wen, Elton | 2023-09-01 | 2023-09-06 | 5 | 100% | bar: WEEK 1 F to WEEK 2 W; WEEK 2 F to WEEK 2 S
1.4 | Formulate questions to ask client during M1 meeting | Lee Suan Hong | 2023-09-01 | 2023-09-03 | 2 | 100% | bar: WEEK 1 F to WEEK 1 S; WEEK 2 F to WEEK 2 S
1.5 | Write M1 meeting minutes | Zames Li ChengYang | 2023-09-07 | 2023-09-07 | 0 | 100% | bar: WEEK 2 T to WEEK 2 S
1.6 | M1 meeting with client | All | 2023-09-07 | 2023-09-07 | 0 | 100% | bar: WEEK 2 T to WEEK 2 S
1.7 | Record the client meeting for future reference | How Shun Han | 2023-09-07 | 2023-09-07 | 0 | 100% | bar: WEEK 2 T to WEEK 2 S
1.8 | Draft meeting minutes email to be sent to client | Lee Suan Hong | 2023-09-07 | 2023-09-11 | 4 | 100% | bar: WEEK 2 T to WEEK 2 S
1.9 | Sending of client meeting minutes to client | Lee Suan Hong | 2023-09-08 | 2023-09-11 | 3 | 100% | bar: WEEK 2 F to WEEK 3 M
1.10 | Creation of Figma share link | Ong Jun Wen, Elton | 2023-09-08 | 2023-09-08 | 0 | 100% | bar: WEEK 2 F to WEEK 2 S
1.11 | Create Project Report | Lee Suan Hong | 2023-09-08 | 2023-09-08 | 0 | 100% | bar: WEEK 2 F to WEEK 2 S
1.12 | Creation of Project Report Section 1 | Zames Li ChengYang | 2023-09-08 | 2023-09-08 | 0 | 100% | bar: WEEK 2 F to WEEK 2 S
1.12.1 | Product scope for M1 report (Section 1) | Zames Li ChengYang | 2023-09-08 | 2023-09-15 | 7 | 100% | bar: WEEK 2 F to WEEK 3 F
1.12.2 | Related background literature for M1 report (Section 1) | Zames Li ChengYang | 2023-09-08 | 2023-09-15 | 7 | 100% | bar: WEEK 2 F to WEEK 3 F
1.12.3 | Intended audience and document overview for M1 report (Section 1) | Zames Li ChengYang | 2023-09-08 | 2023-09-15 | 7 | 100% | bar: WEEK 2 F to WEEK 3 F
1.12.4 | References and ackowledgements for M1 report (Section 1) | Zames Li ChengYang | 2023-09-08 | 2023-09-15 | 7 | 100% | bar: WEEK 2 F to WEEK 3 F
1.13 | Creation of Project Report Section 2 | Ong Jun Wen, Elton | 2023-09-08 | 2023-09-08 | 0 | 100% | bar: WEEK 2 F to WEEK 2 S
1.13.1 | Product Overview for M1 report (Section 2) | Ong Jun Wen, Elton | 2023-09-08 | 2023-09-15 | 7 | 100% | bar: WEEK 2 F to WEEK 3 F
1.13.2 | Product Funtionality for M1 report (Section 2) | Ong Jun Wen, Elton | 2023-09-08 | 2023-09-15 | 7 | 100% | bar: WEEK 2 F to WEEK 3 F
1.13.3 | Activity Diagram for Product Functionality (Section 2) | Ong Jun Wen, Elton | 2023-09-18 | 2023-09-22 | 4 | 100% | bar: WEEK 2 F to WEEK 3 F
1.13.4 | Assumption and Dependencies for M1 report (Section 2) | How Shun Han | 2023-09-08 | 2023-09-15 | 7 | 100% | bar: WEEK 2 F to WEEK 3 F
1.14 | Creation of Project Report Section 3 | Lim Jun Rui | 2023-09-08 | 2023-09-08 | 0 | 100% | bar: WEEK 2 F to WEEK 2 S
1.14.1 | User interface requirements for M1 report (Section 3) | How Shun Han | 2023-09-08 | 2023-09-19 | 11 | 100% | bar: WEEK 2 F to WEEK 4 T
1.14.2 | Functional Requirements for M1 report (Section 3) | Zames Li ChengYang | 2023-09-08 | 2023-09-19 | 11 | 100% | bar: WEEK 2 F to WEEK 4 T
1.14.3 | Use case model/diagram for M1 report (Section 3) | Lee Suan Hong | 2023-09-08 | 2023-09-19 | 11 | 100% | bar: WEEK 2 F to WEEK 4 T
1.14.4 | Non-functional requirements - performance requirements for M1 report (Section 3) | Lim Jun Rui | 2023-09-08 | 2023-09-19 | 11 | 100% | bar: WEEK 2 F to WEEK 4 T
1.14.5 | Non-functional requirements - safety and security requirements for M1 report (Section 3) | Lim Jun Rui | 2023-09-08 | 2023-09-19 | 11 | 100% | bar: WEEK 2 F to WEEK 4 T
1.14.6 | Other requirements for M1 report (Section 3) | Lee Suan Hong | 2023-09-08 | 2023-09-19 | 11 | 100% | bar: WEEK 2 F to WEEK 4 T
1.15 | Creation of Project Report Section 4 | How Shun Han | 2023-09-14 | 2023-09-14 | 0 | 100% | bar: WEEK 2 F to WEEK 2 S; WEEK 3 T
1.15.1 | Project estimation and plan - software estimation for M1 report (Section 4) | How Shun Han | 2023-09-14 | 2023-09-21 | 7 | 100% | bar: WEEK 2 F to WEEK 2 S; WEEK 3 T to WEEK 4 T
1.15.2 | Project estimation and plan - project management for M1 report (Section 4) | How Shun Han | 2023-09-14 | 2023-09-21 | 7 | 100% | bar: WEEK 2 F to WEEK 2 S; WEEK 3 T to WEEK 4 T
1.16 | Creation of Project Report Section 5 | Lim Jun Rui | 2023-09-08 | 2023-09-08 | 0 | 100% | bar: WEEK 2 F to WEEK 2 S
1.16.1 | Use case model/diagram description for M1 report (Section 5) | Lim Jun Rui | 2023-09-08 | 2023-09-19 | 11 | 100% | bar: WEEK 2 F to WEEK 4 T
1.17 | Creation of Project Report Section 6 | Lim Jun Rui | 2023-09-08 | 2023-09-08 | 0 | 100% | bar: WEEK 2 F to WEEK 2 S
1.17.1 | Data dictionary (Section 6) | Lim Jun Rui | 2023-09-08 | 2023-09-19 | 11 | 100% | bar: WEEK 2 F to WEEK 4 T
1.18 | Submission of M1 Report | Ong Jun Wen, Elton | 2023-09-21 | 2023-09-23 | 2 | 100% | bar: WEEK 2 F to WEEK 2 S; WEEK 4 T to WEEK 4 S
2 | M2
2.1 | Creation of M2 Report | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
2.1.1 | Component Design - M2 Report | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
2.1.2 | Class Diagram - M2 Report | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
2.1.3 | Sequence Diagram - M2 Report | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
2.2 | Submission of M2 Report | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
2.3 | M2 Presentation of Class, Component, and Sequence Diagram | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
3 | M3
3.1 | Creation of M3 Report | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
3.2 | Black-box Testing | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
3.3 | White-box Testing | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
3.4 | Prototyping | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S
3.5 | Submission of M3 Report | TBD |  |  | 0 | 0% | bar: WEEK 2 F to WEEK 2 S